Project Overview - Nexus Platform Modernization

Horizon Credentialing Services (fictional)

SYNTHETIC PORTFOLIO DATASET - All organizations, people, dates, metrics and events are fictional.

# 1. Project Summary

| Field | Details |
| --- | --- |
| Project Name | Nexus Platform Modernization |
| Client | Horizon Credentialing Services |
| Delivery Partner | Meridian Digital Solutions |
| Commercial Model | Fixed price - two phases |
| Kick-off Date | 06-Jan-2026 |
| Phase 1 Baseline | Modernized platform UAT sign-off by 30-Jun-2026 |
| Phase 2 Baseline | Identity/data migration and optimization by 30-Sep-2026 |
| Program Manager | Alex Morgan |
| Client Product Lead | Maya Collins |

# 2. Business Objective and Scope

Modernize the legacy credentialing portal while maintaining functional parity for high-volume operational workflows.

Move the application to a supported technology stack using .NET 8, Angular, Azure-hosted services, and SQL Server.

Retain the familiar desktop-style Admin experience during Phase 1 to reduce operational disruption; broader UX redesign is deferred.

Integrate with external identity, course, exam, billing, notification, and learning systems through APIs/events.

Phase 2 includes identity-data migration, technical debt reduction, performance optimization, and selected workflow simplification.

# 3. Key Personas and Workflows

| Persona | Representative Workflows |
| --- | --- |
| Candidate | Invitation, first login, course enrollment, exam scheduling, achievement history |
| Faculty | Course acceptance, learner roster, exam setup, status review |
| Admin | User/role management, course setup, certification maintenance, reporting, exception handling |

# 4. Architecture Guardrails

Single deployable application for the modernized portal, with internal modules kept in one repository unless there is a clear reuse case.

One CI/CD pipeline deploys front-end and back-end together; main branch must remain deployable.

SQL Server is the target database, with temporary dual-database compatibility permitted during transition.

External integrations use REST APIs or event messaging; environment-specific credentials and endpoints are managed outside source code.

Admin screens preserve legacy navigation; public-facing screens follow the enterprise design system and accessibility standards.

# 5. Initial Milestones

| Milestone | Baseline Date | Exit Criteria |
| --- | --- | --- |
| Environment and CI/CD ready | 20-Feb-2026 | Dev/QA/Stage deployable through pipeline |
| Application-wide demo | 27-Mar-2026 | Core Candidate/Faculty/Admin flows demonstrated |
| Phase 1 feature complete | 22-May-2026 | Functional parity scope completed |
| UAT start | 15-Jun-2026 | Production-like environment stable; no open Sev-1 blockers |
| Phase 1 UAT sign-off | 30-Jun-2026 | Critical scenarios passed; agreed defects dispositioned |
| Phase 2 complete | 30-Sep-2026 | Migration utility live; performance and stabilization targets met |

# 6. Success Measures

No Severity-1 defects at UAT entry and at least 95% pass rate across agreed critical regression scenarios.

P95 response time below 2.5 seconds for the top 20 transactional workflows under agreed load.

No data-loss defects during migration rehearsal and production cutover.

WCAG 2.1 AA compliance for external-facing screens included in Phase 1.