Meeting Minutes - Architecture and Delivery Standards

18-May-2026 | Nexus Platform Modernization

SYNTHETIC PORTFOLIO DATASET - All organizations, people, dates, metrics and events are fictional.

| Meeting Detail | Value |
| --- | --- |
| Date | 18-May-2026 |
| Purpose | Confirm technical guardrails and readiness approach before Phase 1 closure |
| Attendees | Alex Morgan (Program Manager); Maya Collins (Client Product); Ethan Brooks (Client Architecture); Sofia Ramirez (Delivery Engineering); Liam Foster (QA); Chloe Bennett (UX) |

# 1. Decisions and Consensus

Application structure: keep Nexus as a single deployable application for Phase 1. Integration with enterprise services will continue through REST APIs and event messaging.

Repository: use one root solution and keep project-specific helper libraries in the same repository. Shared packages should be introduced only where there is a proven cross-product need.

Deployment: one pipeline must deploy the full application. Teams will favor small commits and keep the main branch releasable.

Database: SQL Server remains the target. During transition, selected services may temporarily read from the legacy PostgreSQL database until synchronization is proven.

Admin UX: preserve the legacy information architecture and menu order for Phase 1; use the enterprise component library underneath. External-facing login and candidate screens must follow the modern design system.

Testing: temporary diagnostic endpoints must not remain in production code. Automated unit/integration tests will replace manual test controllers before release.

# 2. Open Questions / Dependencies

| Dependency | Owner | Needed By | Status | Notes |
| --- | --- | --- | --- | --- |
| Identity Service admin-role API contract | Client Identity Team | 22-May-2026 | Open | Swagger is available; final permission model still needs confirmation. |
| QA/Stage database owner permissions | Client Platform Team | 20-May-2026 | In Progress | Read access exists; schema migration requires elevated rights. |
| Enterprise design-system mapping for legacy buttons | Client UX | 25-May-2026 | Open | Needed to resolve primary/secondary/tertiary action patterns. |
| Performance-test responsibility confirmation | Program Leadership | 21-May-2026 | Open | Scope ownership must be confirmed before load-test planning is finalized. |

# 3. Action Items

| Action | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Share finalized admin-role API examples and permission IDs | Ethan Brooks | 22-May-2026 | Open |
| Provide database schema-owner access for QA and Stage | Maya Collins | 20-May-2026 | In Progress |
| Publish migration scripts to repository /database/scripts | Sofia Ramirez | 19-May-2026 | Done |
| Share design-system mapping guidance for legacy controls | Chloe Bennett | 25-May-2026 | Open |
| Confirm performance/load-testing scope and ownership | Alex Morgan | 21-May-2026 | Open |