Meeting Minutes - UAT Readiness and Phase 2 Planning

24-Jun-2026 | Nexus Platform Modernization

SYNTHETIC PORTFOLIO DATASET - All organizations, people, dates, metrics and events are fictional.

| Meeting Detail | Value |
| --- | --- |
| Date | 24-Jun-2026 |
| Purpose | Review UAT readiness, production dependencies, and Phase 2 scope changes |
| Attendees | Alex Morgan; Maya Collins; Ethan Brooks; Sofia Ramirez; Liam Foster; Noah Patel (Client Identity); Ryan Kim (SRE) |

# 1. UAT Readiness Update

UAT cannot begin on the previously planned 29-Jun date because the legacy production deployment was rolled back after performance-test instability.

The modernized portal depends on the legacy deployment for selected background jobs, service redirects, and third-party integrations; production-like sanity cannot complete until legacy is stable.

A certification blackout window on 27-28 Jun also prevents production changes. The working UAT start date is now 06-Jul-2026, subject to legacy deployment completion.

One blocker remains on the invoice-export workflow and six major/critical issues remain distributed across both teams.

# 2. Phase 2 Scope Change

Original Phase 2 intent was platform stabilization, performance optimization, and reduction of technical debt.

The client has now requested an additional migration utility to move learner entitlement data from the legacy Learning Hub to the Unified Identity Service.

The delivery team will not baseline Phase 2 estimates until the Identity Team provides API access, field-level mapping, error-handling expectations, and sample data.

Program leadership agreed that this is a material scope change and must be reflected in the change log and revised milestone plan.

# 3. Decisions

| Decision | Outcome |
| --- | --- |
| UAT start | Target 06-Jul-2026, conditional on successful legacy production deployment and smoke test. |
| Phase 1 sign-off | Tentatively moved to 17-Jul-2026; final date will be baselined after first three days of UAT. |
| Phase 2 migration utility | Include in scope subject to impact assessment and written approval. |
| Accessibility testing | Run in parallel with UAT for candidate-facing screens; blocking issues remain release criteria. |

# 4. Action Items

| Action | Owner | Due Date | Status | Notes |
| --- | --- | --- | --- | --- |
| Redeploy legacy application after performance fixes | Ryan Kim | 03-Jul-2026 | Open | Must complete before modernized production sanity. |
| Share Unified Identity API access and sandbox credentials | Noah Patel | 29-Jun-2026 | Open | Required for Phase 2 analysis. |
| Provide migration field mapping and sample payloads | Maya Collins | 30-Jun-2026 | Open | Include invalid/duplicate cases. |
| Prepare impact assessment for migration utility | Sofia Ramirez | 03-Jul-2026 | Open | Estimate effort, timeline, testing and data-reconciliation needs. |
| Publish revised integrated milestone plan | Alex Morgan | 07-Jul-2026 | Open | After UAT start is confirmed. |