Weekly Status Report

Week: 08-Jun-2026 to 12-Jun-2026 | NexusCert Platform Modernization

SYNTHETIC PORTFOLIO DATASET - All organizations, people, dates, metrics and events are fictional.

| RAG Status | Previous Week | This Week |
| --- | --- | --- |
| Status | Amber | Red |

# 1. Project Summary

| Field | Details |
| --- | --- |
| Project Type | Fixed Price |
| Kick-off Date | 06-Jan-2026 |
| Planned Phase 1 UAT Start | 15-Jun-2026 |
| Planned Phase 1 Sign-off | 30-Jun-2026 |
| Phase 2 Completion | 30-Sep-2026 |
| Program Manager | Alex Morgan |

# 2. Executive Summary

RAG moved from Amber to Red because UAT is planned to start on 15-Jun, while production-readiness dependencies remain unresolved.

The production-like environment is deployed, but an invoice-export defect and an identity-role issue are still blocking critical workflows.

Legacy/modern database differences identified during rehearsal require remediation before end-to-end validation can be completed.

Phase 2 analysis has not started because Unified Identity API access and technical mapping are still pending.

# 3. Project Metrics

| Work Queue | Client Dev | Delivery Dev | Delivery QA | Client QA | On Hold | Resolved | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Issue Count | 8 | 5 | 6 | 2 | 2 | 63 | 86 |

# 4. Forces of Change

| Question | Yes/No | Explanation |
| --- | --- | --- |
| Have time/quality assumptions changed? | Yes | Additional end-to-end validation is required because production and staging database schemas are not fully aligned. |
| Is an upcoming milestone at risk? | Yes | UAT start on 15-Jun is at risk unless two blockers are closed and production sanity completes. |
| Are there major external dependencies? | Yes | Identity-role API clarification and client-side invoice integration fix are pending. |

# 5. Key Updates This Week

Completed application-wide regression on the latest Stage build; 14 issues were closed after retest.

Implemented 180+ schema-alignment changes identified between legacy reference data and the modernized database.

Performance tuning reduced median page-load time by approximately 18% in QA; full load test is still pending.

Candidate invitation, course enrollment, exam setup, and achievement-history flows are stable in Stage.

# 6. Dependencies / Support Required

| Dependency | Support Required | Owner | Target | Status |
| --- | --- | --- | --- | --- |
| Invoice export integration | Client team to resolve downstream validation failure | Client Integration | 15-Jun | Open |
| Identity admin-role API | Confirm permission model and provide working sample | Client Identity | 13-Jun | Open |
| Production database alignment | Provide final schema delta and approve scripts | Client DBA | 13-Jun | In Progress |
| UAT business testers | Confirm named testers and availability | Client Product | 12-Jun | Done |

# 7. Upcoming Activities

Close remaining blockers and execute production-like sanity.

Start UAT on 15-Jun if entry criteria are met; otherwise publish revised date within one business day.

Finalize go-live/cutover approach for Phase 1.

Schedule Phase 2 technical workshop with the Unified Identity team.

# 8. Top Risks

| Risk | Mitigation | Owner | Status |
| --- | --- | --- | --- |
| UAT delay due to unresolved integration blockers | Daily cross-team defect triage; escalate blockers older than 48 hours. | Alex Morgan | High |
| Phase 2 start delayed by missing Identity API/mapping | Leadership escalation; do not baseline estimates until inputs are complete. | Maya Collins | High |