Weekly Status Report

Week: 22-Jun-2026 to 26-Jun-2026 | NexusCert Platform Modernization

SYNTHETIC PORTFOLIO DATASET - All organizations, people, dates, metrics and events are fictional.

| RAG Status | Previous Week | This Week |
| --- | --- | --- |
| Status | Red | Red |

# 1. Project Summary

| Field | Details |
| --- | --- |
| Project Type | Fixed Price |
| Kick-off Date | 06-Jan-2026 |
| Current UAT Start | 06-Jul-2026 (working date) |
| Tentative Phase 1 Sign-off | 17-Jul-2026 |
| Phase 2 Completion | 30-Sep-2026 - at risk |
| Program Manager | Alex Morgan |

# 2. Executive Summary

Project remains Red. The previously revised UAT date of 29-Jun is no longer achievable because the legacy production deployment was rolled back after performance instability.

A planned certification blackout on 27-28 Jun further limits the production-change window. The current working UAT start is 06-Jul, subject to successful legacy redeployment.

The number of open defects has reduced materially, but production sanity is blocked until the legacy platform is stable.

Phase 2 scope now includes a requested learner-entitlement migration utility. Estimation is pending API access, field mapping, and sample data from the client Identity team.

# 3. Issue Metrics

| Severity | Client Dev | Delivery Dev | Delivery QA | Client QA | On Hold | Resolved | Cancelled | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Blocker | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 13 |
| Critical / Major | 2 | 1 | 1 | 1 | 1 | 24 | 1 | 31 |
| Medium / Minor | 1 | 3 | 2 | 1 | 0 | 52 | 1 | 60 |
| Total | 4 | 4 | 3 | 2 | 1 | 88 | 2 | 104 |

# 4. Forces of Change

| Question | Yes/No | Explanation |
| --- | --- | --- |
| Have project objectives/scope/time changed? | Yes | Phase 1 timing moved due to production dependency; Phase 2 now includes a migration utility not in the original baseline. |
| Are upcoming milestones at risk? | Yes | UAT and Phase 1 sign-off are dependent on the 03-Jul legacy redeployment. |
| Will project completion be missed? | Potentially | Phase 2 completion is at risk until scope impact and Identity API dependencies are resolved. |

# 5. Key Updates This Week

Closed 11 defects after joint validation; the remaining blocker is the invoice-export workflow.

Completed cross-browser validation for Chrome and Edge; Safari validation is 70% complete.

Accessibility test execution started for candidate-facing screens; two medium issues were logged.

Completed first-pass analysis of the requested entitlement migration utility; requirements remain incomplete.

# 6. Dependencies / Support Required

| Dependency | Support Required | Owner | Target | Status |
| --- | --- | --- | --- | --- |
| Legacy production deployment | Complete performance fixes and redeploy | Client SRE | 03-Jul | Open |
| Unified Identity APIs | Provide sandbox access and endpoint list | Client Identity | 29-Jun | Open |
| Migration mapping | Provide source-to-target field map and sample records | Client Product | 30-Jun | Open |
| Invoice export blocker | Validate client-side fix in Stage | Client Integration | 30-Jun | In Progress |

# 7. Upcoming Activities

Validate legacy redeployment and execute integrated production sanity.

Start UAT on 06-Jul if entry criteria are met.

Complete accessibility validation for candidate-facing flows.

Produce Phase 2 migration-utility impact assessment after API and mapping inputs are received.

# 8. Top Risks

| Risk | Mitigation | Owner | Status |
| --- | --- | --- | --- |
| Phase 1 UAT delay due to legacy production dependency | Daily SRE checkpoint; keep rollback plan and smoke suite ready for same-day execution. | Alex Morgan | High |
| Phase 2 timeline impact from scope expansion | Log formal change; estimate only after API/mapping inputs; seek milestone re-baseline if approved. | Alex Morgan | High |
| Late client validation causes rework near UAT | Daily defect aging review and 24-hour SLA for blocker/critical validation. | Maya Collins | Medium |