## Dependencies
Dependency ID | Category | Dependency / Description | Owner | Due Date | Status | Resolved On | Impact | Notes
DEP-001 | Access & Environment | Identity Service sandbox access for admin-role testing | Client Identity | 2026-05-22 | Resolved | 2026-05-23 | Medium | Sandbox credentials issued; role-assignment examples still required.
DEP-002 | Access & Environment | QA and Stage database schema-owner permissions | Client Platform | 2026-05-20 | Resolved | 2026-05-21 | High | Elevated rights granted for controlled schema deployment window.
DEP-003 | Architecture | Final admin-role API contract and permission mapping | Client Identity | 2026-05-22 | Resolved | 2026-05-27 | High | Swagger updated with role and permission examples.
DEP-004 | Design & UX | Design-system mapping for legacy-style admin controls | Client UX | 2026-05-25 | Resolved | 2026-05-26 | Low | Primary/secondary/tertiary action guidance shared.
DEP-005 | Testing | Confirmation of performance/load-testing ownership | Program Leadership | 2026-05-21 | Resolved | 2026-05-22 | Medium | Delivery team executes tests; client SRE provides production-like environment support.
DEP-006 | Environment | Production database schema delta and final alignment scripts | Client DBA | 2026-06-13 | Resolved | 2026-06-14 | High | Final schema comparison completed and scripts approved.
DEP-007 | Integration | Invoice export downstream validation fix | Client Integration | 2026-06-15 | In Progress |  | High | Single remaining blocker for Phase 1 UAT entry.
DEP-008 | Release | Legacy production deployment required before modernized production sanity | Client SRE | 2026-07-03 | Open |  | Critical | Previous deployment rolled back after performance instability.
DEP-009 | Testing | Named UAT business testers and availability | Client Product | 2026-06-12 | Resolved | 2026-06-12 | Medium | Eight business testers confirmed.
DEP-010 | Phase 2 | Unified Identity API sandbox access and endpoint list | Client Identity | 2026-06-29 | Open |  | High | Required to estimate and start Phase 2 migration utility.
DEP-011 | Phase 2 | Source-to-target field mapping for learner-entitlement migration | Client Product | 2026-06-30 | Open |  | High | Must include duplicate, inactive, and invalid-record scenarios.
DEP-012 | Phase 2 | Representative sample data for migration rehearsal | Client Product | 2026-06-30 | Open |  | Medium | Synthetic sample is acceptable for development; masked production sample needed later.
DEP-013 | Environment | Safari browser device coverage for candidate portal | Client QA | 2026-07-02 | In Progress |  | Low | Execution 70% complete as of 26-Jun.
DEP-014 | Accessibility | Accessibility review for candidate-facing screens | Delivery QA | 2026-07-06 | In Progress |  | Medium | Two medium issues logged; no blocker identified.

## Risks_Issues
ID | Type | Description | Date Identified | Owner | Probability | Impact | Status | Mitigation / Next Step | Target Review
R-001 | Risk | UAT start may slip if legacy production deployment is not stable. | 2026-06-18 | Alex Morgan | High | High | Open | Daily SRE checkpoint; execute smoke suite immediately after redeploy; keep rollback plan ready. | 2026-07-03
I-002 | Issue | Invoice export fails downstream validation for one production-like workflow. | 2026-06-10 | Client Integration | N/A | Critical | In Progress | Client integration team to deploy fix to Stage and complete joint validation. | 2026-06-30
R-003 | Risk | Phase 2 timeline may be missed because Identity APIs and data mapping are not yet available. | 2026-06-08 | Maya Collins | High | High | Open | Leadership escalation; do not baseline estimate until inputs are complete. | 2026-06-30
R-004 | Risk | Late client defect validation could create rework close to UAT. | 2026-06-08 | Maya Collins | Medium | Medium | Open | 24-hour validation target for blocker/critical defects; daily aging review. | 2026-07-01
I-005 | Issue | Legacy production deployment rolled back after load-test instability. | 2026-06-23 | Client SRE | N/A | High | Open | Tune connection pool and background-job concurrency, then rerun 3x load test before redeploy. | 2026-07-03
R-006 | Risk | Migration utility scope may increase Phase 2 effort beyond fixed-price baseline. | 2026-06-24 | Alex Morgan | High | High | Open | Log formal change, prepare impact assessment, and seek written approval before baselining. | 2026-07-07
R-007 | Risk | Candidate-facing accessibility defects may delay release if discovered late. | 2026-06-22 | Liam Foster | Medium | Medium | In Progress | Run accessibility testing in parallel with UAT and treat blocking violations as release criteria. | 2026-07-06
I-008 | Issue | Safari validation is incomplete due to limited device coverage. | 2026-06-25 | Client QA | N/A | Low | In Progress | Reserve device-lab slots and complete remaining candidate workflows. | 2026-07-02

## Actions
Action ID | Source | Action | Owner | Due Date | Status | Completed On | Notes
ACT-001 | Architecture Meeting - 18-May | Share finalized admin-role API examples and permission IDs | Ethan Brooks | 2026-05-22 | Done | 2026-05-27 | Completed five days late; examples added to Swagger.
ACT-002 | Architecture Meeting - 18-May | Provide database schema-owner access for QA and Stage | Maya Collins | 2026-05-20 | Done | 2026-05-21 | Controlled elevated access granted.
ACT-003 | Architecture Meeting - 18-May | Publish migration scripts to repository /database/scripts | Sofia Ramirez | 2026-05-19 | Done | 2026-05-19 | Scripts versioned with rollback notes.
ACT-004 | Architecture Meeting - 18-May | Confirm performance/load-testing scope and ownership | Alex Morgan | 2026-05-21 | Done | 2026-05-22 | Delivery owns execution; Client SRE supports environment.
ACT-005 | WSR - 08-Jun | Confirm UAT business testers and availability | Maya Collins | 2026-06-12 | Done | 2026-06-12 | Eight testers confirmed.
ACT-006 | WSR - 08-Jun | Resolve invoice export downstream validation issue | Client Integration | 2026-06-15 | In Progress |  | Fix under validation.
ACT-007 | UAT/Phase2 Meeting - 24-Jun | Redeploy legacy application after performance fixes | Ryan Kim | 2026-07-03 | Open |  | Entry dependency for modernized production sanity.
ACT-008 | UAT/Phase2 Meeting - 24-Jun | Share Unified Identity API access and sandbox credentials | Noah Patel | 2026-06-29 | Open |  | Escalated after missed initial target.
ACT-009 | UAT/Phase2 Meeting - 24-Jun | Provide migration field mapping and sample payloads | Maya Collins | 2026-06-30 | Open |  | Include invalid and duplicate examples.
ACT-010 | UAT/Phase2 Meeting - 24-Jun | Prepare impact assessment for migration utility | Sofia Ramirez | 2026-07-03 | Open |  | Depends on ACT-008 and ACT-009.
ACT-011 | UAT/Phase2 Meeting - 24-Jun | Publish revised integrated milestone plan | Alex Morgan | 2026-07-07 | Open |  | Will be finalized after UAT actually starts.

## Summary
NexusCert Modernization - Project Control Summary
SYNTHETIC PORTFOLIO DATASET - all names, metrics, dates and events are fictional.
KPI | Value | Dependency Status | Count
Open Dependencies | 4 | Open | 4
Dependencies In Progress | 3 | In Progress | 3
Open Risks / Issues | 8 | Resolved | 7
Open Actions | 5 | On Hold | 0
Actions In Progress | 1
Dataset Design Notes
This workbook is intentionally consistent with the synthetic Project Overview, meeting minutes, and weekly status reports. It includes resolved and unresolved dependencies, evolving milestone risk, scope change, and cross-document action ownership so a retrieval-augmented AI assistant can answer questions that require chronology, status reasoning, and source grounding.